## Slide 1: SL BoG: Main topics
Summary of CCI Papers
Open Issues from previous meeting
Plans of CCI teams for the coming year
Obs4MIPs
CORE-CLIMAX
SAF-CCI interactions
C3S Interactions
Data Portal and toolbox
Optional Extensions
Input to CCI+ position paper
Consistency analysis
COP-21

## Slide 2: Attendance
Represented CCI teams (besides CMUG):
ESA:
  Simon Pinnock and Ed Pechorro
  SSH
  SST
  SI
  IS
  Aerosol
  Cloud
  GHG
  O3
  Fire
  LC
  Glaciers
  SM

## Slide 3: Summary of CCI Papers
  Special issue on the CCI project in Remote Sensing of Environment is now published.
  For the overview paper on uncertainty of CDRs it is proving a challenge to prepare
  It will aim for BAMS and stay generic with lots of references
  Planned schedule is for C. Merchant to draft something in the summer of 2015

## Slide 4: Open Issues from previous meeting
P. Defourny would like to know who is using the land cover open water mask. SST are adopting it and computing distance to land and distance to water. Aerosol, sea-ice and soil moisture also plan to use it. He mentioned there will be a new release of the land water mask in Sept 2015 with user feedback taken into account. Ice sheets may have some input to the water mask.

## Slide 5: Plans of CCI teams for the coming year:
Access to Sentinel data for CCI teams was discussed. Currently all data is kept but at some point there will be a rolling archive. National collaborative ground segments have signed agreements with ESA to download data more quickly. There was some discussions on making Sentinel-1 formats easier to use. For Sentinel-3 there will be the possibility of demonstration products by end of CCI phase 2 but not enough time to integrate into the CCI CDRs. Switzerland has a particular issue with Sentinel data as it is not part of Copernicus. R. Saunders took an action to ask Veronika Eyring if there is a list of which datasets are approved to be used in CMIP6 and how CCI data can be proposed. CMUG was urged to attend CFMIP meetings to promote use of CCI products for CMIP6.

## Slide 6: Obs4MIPs
Datasets from all CCI ECVs will be submitted to Obs4MIPS except Glaciers and Ice sheets are not sure. Teams were encouraged to write a short proposal to Obs4MIPs to check their proposed dataset will be accepted. Victoria Bennett will provide some help to teams for this.

## Slide 7: CORE-CLIMAX
There is a need to provide updates to the maturity matrices towards the end of CCI phase 2. The C3S may use these matrices to assess CDRs so all teams should prepare something.

## Slide 8: SAF-CCI interactions
The next phase of the EUMETSAT SAFs is now in preparation and the draft proposals will soon be written. EUMETSAT have a working group on dataset generation and will meet in June (S. Pinnock will represent CCI). Overlap between the SAF proposals and CCI+ should be avoided as was the case for the sea-ice. The ozone SAF and CMSAF could have potential overlaps if but this is being managed.

## Slide 9: C3S Interactions
All teams to consider which ECVs are mature enough to be proposed for C3S and which need substantial updates. Speakers at the ECMWF workshop include ESA to present the CCI.

## Slide 10: Data Portal and toolbox
Science Leads to provide input to Ed Pechorro on input to the data portal. Toolbox to be started in Autumn.

## Slide 11: Optional Extensions
CMUG has a possible optional extra activity for ice sheet assessments with University of Libre Brussels. No other optional extensions were mentioned.

## Slide 12: Input to CCI+ position paper
All science leads urged to provide input on the CCI+ position paper which Pascal has circulated. It is anticipated that ‘old’ ECVs won’t be in CCI+. However new products are possible (e.g. ocean colour for class 2 waters). How new Sentinel data will be incorporated for CCI+ is not yet clear.

## Slide 13: Consistency analysis
T. Holzer-Popp reported on the table of a consistency analysis between ECVs planned and he will send out a table to prompt input for this.

## Slide 14: COP-21
It was requested that ESA make science leads aware if they will be required to attend the COP-21 meetings in Paris.